## Summary
A320neo FMS Trainer - Phase 2 & 3 Implementation Audit
Metadata
Aircraft Engine Rating | 132 kN | Source: Target_work.md Appendix A.1 (LEAP-1A)
Audit Date | 2026-07-13 | Source: System Clock
Auditor Role | Independent Quality Auditor | Source: Task Specification
Test Suite Outcome | PASS (16/16 test suites) | Source: FmsTests.exe run
System Status Checklist Summary
System/Component | Audit Category | Status | Source File / Context
Hydraulic Pressures / RAT / PTU / Braking Cascade | Phase 2 Core Systems | Completed | SystemsManager.cpp:123-176
Electrical Bus Topology (AC1->AP1 coupling, ESS SHED) | Phase 2 Core Systems | Completed | SystemsManager.cpp:178-246
Feed SystemsManager real inputs (Engine N1/N2/IDG) | Phase 2 Core Systems | Completed | SystemsManager.cpp:128-129, 184-185
updateFuel() pump logic, crossfeed, per-tank burn | Phase 2 Core Systems | Completed | SystemsManager.cpp:248-347
APU: Real start, run, EGT model | Phase 2 Core Systems | Completed | SystemsManager.cpp:61-92
ADIRS: ALIGN, NAV, ATT degraded mode | Phase 2 Core Systems | Completed | SystemsManager.cpp:94-121
OverheadPanel.qml switches wiring | Phase 2 Core Systems | Completed | OverheadPanel.qml:23-55
ECAM SD pages live SystemsManager values | Phase 2 Core Systems | Completed | SystemStatus.qml:1-150
EngineModel internals: N1/N2 spools, start sequence | Phase 3 Engine Model | Completed | EngineModel.cpp
ThrottleQuadrantModel skeleton | Phase 3 Engine Model | Started | ThrottleQuadrantModel.hpp
GroundModel skeleton | Phase 3 Ground Model | Started | GroundModel.hpp
Total Completed Items
Total Started Items
Total Items Audited